## Mutual action plan
Mutual action plan
Build it backwards from the buyer's date. Every line needs a buyer owner. Security and legal start right after the NDA and run in parallel with the evaluation. Keep completed steps with the date they were done.
Stream | Step | Buyer owner | Our owner | Target date | Status | Done on
Header | Desired outcome and the buyer's target date (and why that date) |  |  |  | Open
Header | Go-live date |  |  |  | Open
Header | Signature date (go-live minus implementation time) |  |  |  | Open
Evaluation | Discovery complete and summary agreed |  |  |  | Open
Evaluation | Solution workshop with users |  |  |  | Open
Evaluation | Proof of concept with written success criteria (only if needed) |  |  |  | Open
Evaluation | Reference call |  |  |  | Open
Business case | Value model built with the buyer's own numbers |  |  |  | Open
Business case | Reviewed by finance |  |  |  | Open
Business case | Approved by the economic buyer |  |  |  | Open
Security and data | Security pack sent (start right after the NDA) |  |  |  | Open
Security and data | Security questionnaire completed |  |  |  | Open
Security and data | Data protection review and sub-processor check |  |  |  | Open
Legal | Standard terms sent (start right after the NDA) |  |  |  | Open
Legal | Redlines agreed |  |  |  | Open
Procurement | Vendor onboarding |  |  |  | Open
Procurement | Purchase order raised |  |  |  | Open
Signature | Named signer signs |  |  |  | Open
After signature | Kick-off held |  |  |  | Open
After signature | First value milestone reached |  |  |  | Open
Steps slipped
Steps done
salesmotion.io ¦ Free template. Copy, adapt and share.

## Worked example
Worked example: dating from a February-to-January fiscal year
Illustrative. A buyer whose financial year ends 31 January wants the project funded from this year's budget. Work back from that date.
Stream | Step | Target date | Note
Header | Budget must be committed before fiscal year end | 31 Jan | From the buyer's annual report
Signature | Contract signed | 23 Jan | One week of buffer
Procurement | Purchase order raised | 16 Jan
Legal | Redlines agreed | 9 Jan | Started at the NDA in November
Security and data | Questionnaire and data protection review complete | 19 Dec | Started at the NDA, in parallel
Business case | Approved by the economic buyer | 5 Dec | Holiday period: approvals slow down
Business case | Reviewed by finance | 28 Nov
Evaluation | Solution workshop with users | 14 Nov
Evaluation | Discovery complete and summary agreed | 7 Nov
salesmotion.io ¦ Free template. Copy, adapt and share.